## Project Timeline
Project Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date | Milestone | Assigned To | Position | Baseline | Kolonne1 | Project Timeline Tip
2022-02-01 | Project Start |  | 10 | 0 |  | Use the Position field in the Project Milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2022-02-21 | Systembeskrivelse |  | 20 | 0
2022-03-14 | Component models 5/10 |  | 20 | 0
2022-03-21 | Component models 10/10 |  | 10 | 0
2022-03-25 | Courses done |  | -10 | 0
2022-04-13 | Model done |  | 10 | 0
2022-04-14 | Påske start |  | -10 | 0
2022-04-17 | Påske slut |  | -15 | 0
2022-04-20 | Controller design - not mpc |  | 20 | 0
2022-04-29 | Controller design - mpc |  | 10 | 0
2022-05-10 | Robust controller design |  | 20 | 0
2022-05-17 | Test simulation / benchmark |  | 10 | 0
2022-05-25 | Project done |  | 20 | 0
2022-06-01 | Project delivery |  | -10 | 0
0